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	A. 
	Physical Progress of Dam Package Works as on Oct’2025 (completion in %age terms):

	1. 
	Diversion Tunnel (Excavation & Lining)
	100%

	2. 
	Upstream & Downstream Coffer Dams
	100%

	3. 
	Concrete Faced Rockfill Dam
	74% 

	4. 
	Head Race Tunnel (DBM) Excavation
	100%

	5. 
	Head Race Tunnel 02 Nos. (DBM) Overt Lining
	83%

	6. 
	Tunnel Spillway Excavation - 02 Nos.
	100%

	7. 
	Tunnel Spillway Overt Lining – 02 Nos.		
	1% (Lining works has been commenced on 28.10.2025.)

	8. 
	Tunnel Spillway Gate Shaft(s) Platform
	100%

	9. 
	Tunnel Spillway Gate Shaft(s) Exc. – 02 Nos.
	98%

	10. 
	Tunnel Spillway Gate Shaft(s) Lining – 02 Nos.
	Linked with HM works i.e. erection of Steel Liner in TSPs.

	11. 
	Surface Spillway Excavation
	100%

	12. 
	Surface Spillway Concreting
	8%

	13. 
	Power Intake Surface Excavation
	91%

	14. 
	Power Intake Concreting
	To be taken up from Dec’2025

	15. 
	Power Intake Gate Shaft(s) Platform
	100% 

	16. 
	Power Intake Gate Shaft(s) Excavation– 04 Nos.
	100%

	17. 
	Power Intake Gate Shaft(s) Concreting– 04 Nos.
	To be taken up from mid Dec’2025 and the same is linked with HM works of Gate Shaft(s).

	B. 
	Physical Progress of Power House Package Works as on Oct’2025 (completion in %age terms):

	1. 
	Excavation of Power House, TH, MIV and its Adits
	100%

	2. 
	Concreting of Power House
	99%

	3. 
	Concreting of Transformer Hall
	100%

	4. 
	Concreting of MIV
	93%

	5. 
	Excavation of Ventilation cum Cable Tunnel
	100%

	6. 
	Over Lining of Ventilation cum Cable Tunnel
	99%

	7. 
	Excavation of Busduct
	100%

	8. 
	Concreting of Busduct
	100%

	9. 
	Tail Race Tunnel Adits
	100%

	10. 
	Tail Race Tunnel Excavation
	77%

	11. 
	Tail Race Tunnel Concreting
	40%

	12. 
	Tail Race Tunnel Outlet (Excavation)
	100%

	13. 
	Tail Race Tunnel Outlet (Concrete)
	87%

	14. 
	Access Tunnel to Pressure Shaft Top
	100%

	15. 
	Excavation of Pressure Shafts
	100%

	16. 
	Adits of Valve House
	100%

	17. 
	Valve House (Excavation)
	100%

	18. 
	Valve House (Concreting)
	96%

	19. 
	Switchyard (Excavation)
	100%

	20. 
	Switchyard (Concreting)
	55%	

	21. 
	Surge Shaft Access & Adits
	100%

	22. 
	Surge Shaft Excavation
	50% 

	23. 
	Surge Shaft Lining
	To be taken up from Dec’2025

	C. 
	Physical Progress of HRT-TBM Package Works as on Oct’2025 (completion in %age terms):

	1. 
	HRT Adits
	100%

	2. 
	HRT-1 Excavation & Lining
	69%

	3. 
	HRT-2 Excavation & Lining
	60%

	4. 
	Segments Casting
	72%

	D. 
	Physical Progress of HM Package Works as on Oct’2025 (completion in %age terms):

	1. 
	Steel Liner in Lower Horizontal Portion
	100%

	2. 
	Steel Liner in Top Horizontal Portion
	95%

	3. 
	Steel Liner in Bifurcation of Pressure Shafts
	100%

	4. 
	Steel Liner in Vertical Pressure Shafts
	50%

	5. 
	Steel Liner in Tunnel Spillway(s)
	4%

	6. 
	Steel Liner in Tunnel Spillway Gate Shaft(s)
	To be taken up in continuity to Steel Liner erection works in TSPs.

	7. 
	Radial Gates in Tunnel Spillway(s)
	To be taken up with Steel Liner erection works of TSPs Gate Shaft(s).

	8. 
	Radial Gates in Surface Spillway
	Linked with Surface Spillway Concreting and shall be taken up in parallel as per the concrete lift.

	9. 
	Power Intake Trash Rack
	Linked with Power Intake concreting and shall be taken up in parallel to concreting works.

	10. 
	Power Intake Bulkhead Gate(s) – 2 Nos.
	To be taken up in phased manner from mid Dec’2025.

	11. 
	Power Intake Service Gate(s) – 2 Nos.
	To be taken up in phased manner from mid Dec’2025.

	E. 
	Physical Progress of E&M Package Works as on Oct’2025 (completion in %age terms):

	1. 
	Supply of E&M Components
	78%

	2. 
	Draft Tube Erection
	100%

	3. 
	Spiral Casing Erection
	100%

	4. 
	Stay Ring Erection
	100%

	5. 
	Pit Liner Erection
	100%

	6. 
	Stator Assembly
	100%

	7. 
	Rotor Assembly
	50%

	8. 
	Lowering of Stator & centering
	75%

	9. 
	Lowering of Distributor and pre-check
	45%

	10. 
	Lowering of Runner with shaft
	50%

	11. 
	Lowering of head cover and final assembly
	50%

	12. 
	Lowering of all major component in turbine pit
	45%

	13. 
	Shaft free
	25%
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