|  |  | Annexure-I |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Physical Progress of Dam Package Works as on Oct’2025 (completion in %age terms): |  |  |  |  |
|  |  | Diversion Tunnel (Excavation & Lining) | 100% |  |  |  |
|  |  | Upstream & Downstream Coffer Dams | 100% |  |  |  |
|  |  | Concrete Faced Rockfill Dam | 74% |  |  |  |
|  |  | Head Race Tunnel (DBM) Excavation | 100% |  |  |  |
|  |  | Head Race Tunnel 02 Nos. (DBM) Overt Lining | 83% |  |  |  |
|  |  | Tunnel Spillway Excavation - 02 Nos. | 100% |  |  |  |
|  |  | Tunnel Spillway Overt Lining – 02 Nos. | 1% (Lining works has been commenced on 28.10.2025.) |  |  |  |
|  |  | Tunnel Spillway Gate Shaft(s) Platform | 100% |  |  |  |
|  |  | Tunnel Spillway Gate Shaft(s) Exc. – 02 Nos. | 98% |  |  |  |
|  |  | Tunnel Spillway Gate Shaft(s) Lining – 02 Nos. | Linked with HM works i.e. erection of Steel Liner in TSPs. |  |  |  |
|  |  | Surface Spillway Excavation | 100% |  |  |  |
|  |  | Surface Spillway Concreting | 8% |  |  |  |
|  |  | Power Intake Surface Excavation | 91% |  |  |  |
|  |  | Power Intake Concreting | To be taken up from Dec’2025 |  |  |  |
|  |  | Power Intake Gate Shaft(s) Platform | 100% |  |  |  |
|  |  | Power Intake Gate Shaft(s) Excavation– 04 Nos. | 100% |  |  |  |
|  |  | Power Intake Gate Shaft(s) Concreting– 04 Nos. | To be taken up from mid Dec’2025 and the same is linked with HM works of Gate Shaft(s). |  |  |  |
|  |  | Physical Progress of Power House Package Works as on Oct’2025 (completion in %age terms): |  |  |  |  |
|  |  | Excavation of Power House, TH, MIV and its Adits | 100% |  |  |  |
|  |  | Concreting of Power House | 99% |  |  |  |
|  |  | Concreting of Transformer Hall | 100% |  |  |  |
|  |  | Concreting of MIV | 93% |  |  |  |
|  |  | Excavation of Ventilation cum Cable Tunnel | 100% |  |  |  |
|  |  | Over Lining of Ventilation cum Cable Tunnel | 99% |  |  |  |
|  |  | Excavation of Busduct | 100% |  |  |  |
|  | Concreting of Busduct |  | 100% |  |  |  |
|  | Tail Race Tunnel Adits |  | 100% |  |  |  |
|  | Tail Race Tunnel Excavation |  | 77% |  |  |  |
|  | Tail Race Tunnel Concreting |  | 40% |  |  |  |
|  | Tail Race Tunnel Outlet (Excavation) |  | 100% |  |  |  |
|  | Tail Race Tunnel Outlet (Concrete) |  | 87% |  |  |  |
|  | Access Tunnel to Pressure Shaft Top |  | 100% |  |  |  |
|  | Excavation of Pressure Shafts |  | 100% |  |  |  |
|  | Adits of Valve House |  | 100% |  |  |  |
|  | Valve House (Excavation) |  | 100% |  |  |  |
|  | Valve House (Concreting) |  | 96% |  |  |  |
|  | Switchyard (Excavation) |  | 100% |  |  |  |
|  | Switchyard (Concreting) |  | 55% |  |  |  |
|  | Surge Shaft Access & Adits |  | 100% |  |  |  |
|  | Surge Shaft Excavation |  | 50% |  |  |  |
|  | Surge Shaft Lining |  | To be taken up from Dec’2025 |  |  |  |
|  | Physical Progress of HRT-TBM Package Works as on Oct’2025 (completion in %age terms): |  |  |  |  |  |
|  | HRT Adits |  | 100% |  |  |
|  | HRT-1 Excavation & Lining |  | 69% |  |  |
|  | HRT-2 Excavation & Lining |  | 60% |  |  |
|  | Segments Casting |  | 72% |  |  |
|  | Physical Progress of HM Package Works as on Oct’2025 (completion in %age terms): |  |  |  |  |  |
|  | Steel Liner in Lower Horizontal Portion |  | 100% |  |  |
|  | Steel Liner in Top Horizontal Portion |  | 95% |  |  |
|  | Steel Liner in Bifurcation of Pressure Shafts |  | 100% |  |  |
|  | Steel Liner in Vertical Pressure Shafts |  | 50% |  |  |
|  | Steel Liner in Tunnel Spillway(s) |  | 4% |  |  |
|  | Steel Liner in Tunnel Spillway Gate Shaft(s) |  | To be taken up in continuity to Steel Liner erection works in TSPs. |  |  |
|  | Radial Gates in Tunnel Spillway(s) |  | To be taken up with Steel Liner erection works of TSPs Gate Shaft(s). |  |
|  | Radial Gates in Surface Spillway |  | Linked with Surface Spillway Concreting and shall be taken up in parallel as per the concrete lift. |  |
|  | Power Intake Trash Rack |  | Linked with Power Intake concreting and shall be taken up in parallel to concreting works. |  |
|  | Power Intake Bulkhead Gate(s) – 2 Nos. |  | To be taken up in phased manner from mid Dec’2025. |  |
|  | Power Intake Service Gate(s) – 2 Nos. |  | To be taken up in phased manner from mid Dec’2025. |  |
|  | Physical Progress of E&M Package Works as on Oct’2025 (completion in %age terms): |  |  |  |  |  |
|  | Supply of E&M Components |  |  | 78% |  |  |
|  | Draft Tube Erection |  |  | 100% |  |  |
|  | Spiral Casing Erection |  |  | 100% |  |  |
|  | Stay Ring Erection |  |  | 100% |  |  |
|  | Pit Liner Erection |  |  | 100% |  |  |
|  | Stator Assembly |  |  | 100% |  |  |
|  | Rotor Assembly |  |  | 50% |  |  |
|  | Lowering of Stator & centering |  |  | 75% |  |  |
|  | Lowering of Distributor and pre-check |  |  | 45% |  |  |
|  | Lowering of Runner with shaft |  |  | 50% |  |  |
|  | Lowering of head cover and final assembly |  |  | 50% |  |  |
|  | Lowering of all major component in turbine pit |  |  | 45% |  |  |
|  | Shaft free |  |  | 25% |  |  |

*******